## Sheet1
Task Number | Planned Action | Planned outcome | Time estimated | Target completion date | Criterion
1 | Brainstorm | Determine Project | 1 week | 2020-10-29 | A
2 | Design Mock Up | Mockup of GUI | 1 week | 2020-12-03 | B
3 | Create Flowchart | Basic logic flowchart for application | 1 day |  | C
4 | Begin coding | Physics Processor 2D implementation (Movement) | 3 days | 2021-02-19 | D
5 | Smooth Out Movement | Delta - Makes the movement move by frames, not seconds | 1 week | 2021-02-24 | D
6 | Create the enviroment the user will come into contact with | Collsions and Move&Slide for borders hitboxes that will be added eventually | 1 day | 2021-02-27 | D
7 | Set up Tree structure with nodes to display the 'World' | Create scene/mainClass for the starting "Main" world. Think of it as a main class. Also Y-sort added for organization on display | 4 days | 2021-03-03 | D
8 | Added visual animations for the player | Animations added with animation player (Up Down Left Right) | 2 days | 2021-03-05 | D
9 | Enviroment is fleshed out to be visually appeling | Background added, Collisions with background "hills" | 2 days | 2021-03-07 | D
10 | State Machine | Use an enum to create idle and attack states for the player. Added Player and Bat to the main scenes. Signals and instancing scenes in the main scene to make connections much more efficient | 2 days | 2021-03-09 | D
11 | Enviroment added more interaction | Hurtboxes and hitboxes added to enemies/grass and the bat and enemy defeated effect. Added a rolling state to give the player an advantage. And stats are added to the bats | 1 day | 2021-03-10 | D
12 | Improve performace, rework logic | Maintainace + bug fixes | 1 week | 2021-03-16 | E
13 | Add interaction from the world to the player. Player stats added + Enemy attack + Player heart UI added to the GUI and "Beat" Bar | Bat IA - Build the object that the clinet is to interact with | 2 days | 2021-03-18 | E
14 | Soft collisions are being detected in existing onjects | Arrays are added to detect the collision that the enemies can have on each other | 1 day | 2021-03-19 | D
15 | Bat IA is conclueded, Player camera, sounds + camera limits |  | 2 days | 2021-03-21 | D
16 | Rythmic battla aspect + Scene changer | Musical aspect of this project added to the player may interacte in a rythmic way if desired and fnilaization of world interaction is expanded to other scenes and data is carried through | 2 days | 2021-03-23 | D
17 | Bug Testing and Upload to CD |  | 1 day | 2021-03-24 | E